## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Estimation | Notes | Date started (or planned) | Date finished (or planned)
TA
TA_01 | Personal Profile Management | As an applicant, I want to maintain a persistent profile with my ID, name, phone number, gender, and other personal information. | Must have | 1 | 1. Personal information can be saved and edited. | 3 | Protecting personal information | Week 1 | Week 2
TA_02 | Vacancy Browsing & Filtering | As an applicant, I want to see the total recruitment quota and current applicant count for each module, so that I can judge my chances and make informed choices. | Must have | 1 | 1. Module list displays "TAs Needed" and "Current Applicants". 2. Real-time updates when new applications are submitted. | 3 | Essential for visibility. | Week 1 | Week 2
TA_03 | Integrated Submission | As an applicant, I want to upload my CV directly within the application form, so that I can complete my application in one go without sending separate emails. | Should have | 2 | 1. Upload button integrated into the form process. 2. Supports .pdf and .docx. 3. Automatic link between the form data and the uploaded file. | 8 | Key Improvement: Removes the manual email workflow. | week3 | week4
TA_04 | Self-Service Password Modification (Logged-in) | As an applicant (TA), I want to modify my password independently when logged in by verifying my current password, so that I can update my password securely without administrator intervention. | Must have | 1 | 1. "Change Password" entry exists in the personal center. 2. System requires current password verification before allowing new password input. 3. New password takes effect immediately after submission. | 5 | Enables self-service password updates; improves user experience and reduces administrator workload. | Week 1 | Week 2
TA_05 | Forgot Password - Online Application | As an applicant (TA) who forgot my password (not logged in), I want to submit a password reset application via the system, so that I can regain account access after administrator verification. | Must have | 1 | 1. "Forgot Password" link is visible on the login page. 2. Application form requires identity verification (student ID, name, registered email/phone). 3. Password is reset to initial "123456" after approval. | 5 | Provides a standardized online path for password recovery; ensures identity verification compliance. | Week 1 | Week 2
TA_06 | Forgot Password - Direct Admin Contact | As an applicant (TA) who forgot my password (not logged in), I want to view the administrator’s official contact information on the forgot password page, so that I can initiate a reset request directly. | Should have | 2 | 1. Administrator’s office phone and official email are clearly displayed on the "Forgot Password" page. 2. System provides a note guiding the direct request process. | 2 | Accelerates urgent password recovery; offers flexible support for users with time-sensitive needs. | week3 | week4
TA_07 | Application Deadline Reminder | As an applicant, I want to receive a reminder notification before the application deadline for a role, so that I don't miss the submission window for my preferred positions. | Could have | 3 | 1. System sends a reminder 48 hours before the deadline to the applicant's registered email/account. 2. Reminder is visible on the dashboard as a pop-up or banner. | 3 | Prevents last-minute rush and missed applications for qualified candidates. | week5 | week6
TA_08 | Document Preview Before Upload | As an applicant, I want to preview my uploaded CV/document before final submission, so that I can confirm the correct file is attached and there are no formatting errors. | Should have | 2 | 1. A preview pane displays the uploaded document (PDF/docx) within the form. 2. Option to re-upload if the preview shows incorrect file/errors. | 5 | Reduces invalid applications due to wrong document uploads. | week3 | week4
TA_09 | Save as Draft | As an applicant, I want to save my progress while filling out the application, so that I can continue later without losing my entered data. | Could have | 3 | 1. "Save Draft" button available on the form. 2. Users can resume unfinished applications from their dashboard. | 3 | Improve the user experience | week5 | week6
TA_10 | Application Status Tracking | As an applicant, I want to see the real-time status of my application, so that I know if I am hired or rejected without contacting the office. | Could have | 3 | 1. A dashboard showing "Submitted", "Reviewing", or "Outcome". 2. Notification upon status change. | 5 | Massive improvement in transparency. | week5 | week6
TA_11 | Application Withdrawal | As an applicant, I want to withdraw a submitted application, so that I can cancel my request if I am no longer available or interested in the role. | Could have | 3 | 1. A "Withdraw" button is visible on the application dashboard. 2. A confirmation prompt appears to prevent accidental withdrawal. | 2 | Clears the recruiter's list of inactive candidates. | week5 | week6
TA_12 | Preference Selection | As an applicant, I want to select up to 3 preferred courses and rank them by priority, so that the recruiter knows my top choices if I am qualified for multiple roles. | Want to have | 4 | 1. User can select up to 3 courses. 2. User can assign "Priority 1, 2, 3" to them. | 3 | Helps the system/recruiter resolve overlaps automatically. | week7 | week8
MO
MO_01 | Manage TA's Work | As a module organizer, I need to fully manage TAs' daily instructional support work in the system, so that I can track work progress clearly and improve the efficiency of instructional support work. | Must have | 1 | 1. Support assigning TA tasks with specified time, requirements and assessment criteria. 2. Enable real-time viewing of TA task status (Not Started/In Progress/Completed/Pending Review). | 8 | Basic requirement, must be done. | week1 | week2
MO_02 | View Questionnaire Submissions | As a module organizer, I need a streamlined way to view questionnaire submissions, so that I can quickly know who enrolled in my course. | Must have | 1 | 1. Support filtering questionnaire submissions by the module organizer’s assigned courses with one click. 2. Ensure filtered student application data is synchronized | 5 | Concern from our teachers | week1 | week2
MO_03 | User Registration & Role Selection | As a module organizer, I want to register an account and select my role, so that I can have the authority to manage TA recruitment. | Must have | 1 | 1. Provide fields for username, password, and role selection (MO). 2. Successfully save user data to a local text/JSON file. | 5 | Foundational for system access. | week1 | week2
MO_04 | Simplify Approval Process | As a module organizer, I need simplified approval processes for TA-related matters, so that I can complete approvals quickly and avoid work delays. | Should have | 2 | 1. Provide a one-stop entrance for all pending approval items. 2. Realize approval tracking and automatic result notifications. | 5 | Improve user using experience | week3 | week4
MO_05 | Optimize UI Design | As a module organizer, I need an optimized system interface, so that I can find functions quickly and complete TA management operations efficiently. | Should have | 2 | 1. Modular interface with prominent core function entrances; support custom shortcuts. 2. Concise layout with rational button placement, no hidden key operations. | 3 | Improve user using experience | week3 | week4
MO_06 | Applicant CV Review | As a module organizer, I want to view and download the CVs submitted by applicants, so that I can evaluate their academic and technical background. | Should have | 2 | 1. Clickable links to CV files (.txt/PDF) in the applicant list. 2. System retrieves files from the designated local path. | 3 | Key for selection process. | week3 | week4
MO_07 | Applicant Selection & Approval | As a module organizer, I want to approve or reject TA applications, so that I can finalize the recruitment for my module. | Should have | 2 | 1. "Approve" and "Reject" buttons for each applicant. 2. Application status updates in the data file. | 3 | Finalizes the recruitment cycle. | week3 | week4
MO_08 | Self-Service Password Modification (Logged-in) | As a module organizer, I want to modify my password independently when logged in by verifying my current password, so that I can update my password securely without administrator intervention. | Must have | 1 | 1. "Change Password" entry exists in the personal center / profile settings. 2. System requires current password verification before allowing new password input. 3. New password complies with system complexity rules and takes effect immediately after submission. 4. No administrator review is required for this path. | 5 | Aligned with TA logged-in self-service change; reduces admin workload for module organizer accounts. | week1 | week2
MO_09 | Forgot Password - Online Application | As a module organizer who forgot my password (not logged in), I want to submit a password reset application via the system, so that I can regain account access after administrator verification. | Must have | 1 | 1. "Forgot Password" link is visible on the login page. 2. Application form requires identity verification (e.g. staff ID / employee number, name, department, registered email or phone). 3. Submission is for administrator to review. 4. After approval, password is reset to initial password 123456 per policy.. | 5 | module organizer counterpart to TA_05; consistent with AD_10 reset-to-123456 and traceability. | week1 | week2
MO_10 | Forgot Password - Direct Admin Contact | As a module organizer who forgot my password (not logged in), I want to view the administrator official contact information on the forgot password page, so that I can request a password reset through phone or email. | Should have | 2 | 1. Administrator’s office phone and official email are clearly displayed on the "Forgot Password" page. 2. System provides a note guiding the direct request process. | 2 | module organizer counterpart to TA_06; supports urgent recovery alongside online application. | week3 | week4
MO_11 | Support Different Course Types | As a module organizer, I need the system to support TA management for different course types, so that I can allocate TA work rationally based on course teaching characteristics. | Want to have | 4 | Support creating/customizing course type tags for new course setup. | 5 | Advanced function | week7 | week8
Admin
AD_01 | Monitor Overall TA Workload | As an Admin, I want to view a dashboard that summarizes the total assigned workload (e.g., weekly hours) of all TAs, so that I can monitor resource allocation and ensure no TA is overloaded. | Must have | 1 | 1. The Admin dashboard shows each TA’s total weekly workload (e.g., total weekly hours) and how many positions/jobs they are assigned to. 2. Supports sorting/filtering (e.g., by TA name or by workload) to spot overloaded TAs. 3. Numbers are calculated from saved job/application records in local text/JSON files (no database). | 5 | Directly addresses the core requirement: “Admin can check TA's overall workload” from the handout. | week1 | week2
AD_02 | Manage System Users | As an Admin, I want to activate, deactivate, or delete user accounts (TA applicants, module organizers), so that I can maintain the system's security and manage the user lifecycle | Must have | 1 | 1. A user management page lists all registered users with their role (TA, module organizer) and account status. 2. Provide action buttons to deactivate a user account.（deactivate的按键在哪里）要加一个 3. Account status changes are reflected in the login system. | 8 | Ensures system integrity and control over the user base | week1 | week2
AD_03 | Oversee Job Postings | As an Admin, I want to view all job postings and have the authority to edit or remove inappropriate content, so that I can ensure all posted vacancies comply with school recruitment policies | Must have | 1 | 1. A page lists all job postings with details (poster, module, posting date). 2. Each posting has “Edit” and “Remove” options available to 没有找到eidt和remove这两个按钮（不是说没有功能，而是按钮本身都没有）要加一个 | 5 | Provides administrative oversight over the content posted by module organizers | week1 | Week 2
AD_04 | View Basic Application Stats | As an Admin, I want to see basic statistics on the recruitment process (e.g., total applications), so that I can understand recruitment trends | Should have | 2 | 1.The admin dashboard shows total applications submitted and number of open/closed positions 2.Data is aggregated from application records. 记录成js文件 | 3 | Simplified stats to reduce development complexity, provides basic reporting data | week3 | week4
AD_05 | Export Core System Data | As an Admin, I want to export core system data (users, jobs, applications) to a file, so that I can create backups | Should have | 2 | 1.An "Export Core Data" button is available in the admin panel （只有basic statistic这一页里有） 2.Clicking it generates a file contained system data（尚未实现） | 5 | Simplified export format to single .csv, meets data backup requirements | week3 | week4
AD_06 | View System Key Event Log | As an Admin, I want to view a log of key system events (e.g., user logins, account status changes), so that I can troubleshoot issues | Could have | 3 | 1.A dedicated log page displays a list of timestamped key events 2.Each log entry includes event type and user ID 3.Logs are written to a local text file | 8 | Simplified log fields, aids in system monitoring and debugging | week5 | week6
AD_07 | Send Bulk Notifications | As an Admin, I want to send notifications to specific roles (simulated via generating a text file), so that I can broadcast important announcements | Could have | 3 | 1.A form allows composing a message and selecting target roles 2.Submitting the form generates a .txt file containing the message and recipient usernames | 8 | Simulates notification with local files, no email server integration needed | week5 | week6
AD_08 | Configure Recruitment Cycle Dates | As an Admin, I want to set application start and end dates, so that I can control the recruitment timeline | Want to have | 4 | 1.A configuration page provides input fields for application start and end dates （setting页的，start在哪里？只看到了deadline） 2.The system auto-enables/disables the "Apply" function based on these dates（apply function具体是什么呢？）（如果已截止，就显示“已截止”；如果没截止，就显示“进行中” | 5 | Simplified to only application dates, adapts to different semester schedules | week7 | week8
AD_09 | Assign Basic User Roles | As an Admin, I want to assign basic roles (TA/module organizer/Admin) to users, so that I can adjust user permissions | Want to have | 4 | 1.An "Assign Basic Role" option is available in the user management list （在user management页的哪里？）就是add new user 2.Upon role change, the user's accessible core features are updated automatically | 5 | Simplified role types to 3 core options, provides basic user account management | week7 | week8
AD_10 | Admin Password Reset Processing | As an administrator, I want to verify TA and Module Organiser ( module organizer) password reset requests (online application or offline contact) and reset passwords to initial password 123456, so that only legitimate users regain account access. | Must have | 1 | 1. System displays pending reset applications with identity information (e.g. student/staff ID, name, department, role TA or MO( module organizer)). 2. After verification, password is reset to 123456. 3. Rejections record a reason and are visible to the applicant where applicable. | 5 | Covers TA_05 and MO_09 online path plus offline MO/TA contact; traceable per security policy. | week1 | week2
AD_11 | Search Users/Jobs | As an Admin, I want to quickly search for users or jobs by name, so that I can efficiently locate management objects | Should have | 2 | 1.A search bar is provided at the top of the user list and job list 2.Supports search by username or job title （只有dashboard, job supervisasion, workload stats有搜索框,可以的） | 3 | Simplified search scope, boosts admin efficiency by reusing list structures | week3 | week4
AD_12 | View Job Application Status Summary | As an Admin, I want to view the application status distribution for a specific job, so that I can monitor recruitment progress | Could have | 3 | 1.The job detail page shows the count of applications in each status (Pending/Approved/Rejected) 2.Data is auto-calculated from application records | 5 | Simplified to status counts, reuses existing application data for oversight | week5 | week6
AD_13 | View Individual User Details | As an Admin, I want to view detailed information of a single user, so that I can check user account status | Should have | 2 | 1.A "View Details" option is available in the user list 2.The detail page displays user's basic info, role, and account status（下图的这些按钮是每个user都有一组的吗？还是说所有的user共用一组？）（这里没问题，每个人都有不一样的按钮）（没问题） | 3 | Basic info view with low development cost, helps admin verify user accounts | week3 | week4