## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Estimation | Notes | Date started (or planned) | Date finished (or planned)
PF_01 | Manage TA's Work | As a professor, I need to fully manage TAs' daily instructional support work in the system, so that I can track work progress clearly and improve the efficiency of instructional support work. | Very High | 1 | 1. Support assigning TA tasks with specified time, requirements and assessment criteria. 2. Enable real-time viewing of TA task status (Not Started/In Progress/Completed/Pending Review). | 8 | Basic requirement, must be done.
PF_02 | View Questionnaire Submissions | As a professor, I need a streamlined way to view questionnaire submissions, so that I can quickly know who enrolled in my course. | Very High | 1 | 1. Support filtering questionnaire submissions by the professor’s assigned courses with one click. 2. Ensure filtered student application data is synchronized in real time. | 5 | Concern from our teachers
PF_03 | User Registration & Role Selection | As a professor, I want to register an account and select my role, so that I can have the authority to manage TA recruitment. | Very High | 1 | 1. Provide fields for username, password, and role selection (MO). 2. Successfully save user data to a local text/JSON file. | 5 | Foundational for system access.
PF_04 | Identity Authentication | As a professor, I want to log in with my credentials, so that I can securely access my module management dashboard. | Very High | 1 | 1. Validate input against the stored user file. 2. Redirect to the teacher-specific interface upon successful login. | 3 | Security requirement.
PF_05 | Job/Task Posting | As a professor, I want to post new TA job openings with detailed requirements, so that students can view and apply for them. | Very High | 1 | 1. Form includes module name, requirements, and responsibilities. 2. Jobs are immediately visible to student users. | 5 | Core business flow.
PF_06 | Support Mobile Device | As a professor, I need full mobile adaptation of the system, so that I can handle TA management work anytime in non-computer scenarios. | High | 1 | 1. Realize all computer-side viewing functions for core TA management data on mobile. 2. Achieve real-time data synchronization between mobile and computer ends. | 8 | Useful improvement |  |  | 需要吗？
PF_07 | Simplify Approval Process | As a professor, I need simplified approval processes for TA-related matters, so that I can complete approvals quickly and avoid work delays. | High | 1 | 1. Provide a one-stop entrance for all pending approval items. 2. Realize real-time approval tracking and automatic result notifications. | 5 | Improve user using experience
PF_08 | Optimize UI Design | As a professor, I need an optimized system interface, so that I can find functions quickly and complete TA management operations efficiently. | High | 1 | 1. Modular interface with prominent core function entrances; support custom shortcuts. 2. Concise layout with rational button placement, no hidden key operations. | 3 | Improve user using experience
PF_09 | Increase System Stability | As a professor, I need a highly stable system, so that I can complete TA management work smoothly and ensure work continuity. | High | 1 | 1. Core page loading less than 2s for computer, 3s for mobile, no long-term loading failures. 2. Support ≥100 concurrent logins in peak periods with no freezes/data errors. | 5 | Avoid system breakdown
PF_10 | Applicant CV Review | As a professor, I want to view and download the CVs submitted by applicants, so that I can evaluate their academic and technical background. | High | 1 | 1. Clickable links to CV files (.txt/PDF) in the applicant list. 2. System retrieves files from the designated local path. | 3 | Key for selection process.
PF_11 | Applicant Selection & Approval | As a professor, I want to approve or reject TA applications, so that I can finalize the recruitment for my module. | High | 1 | 1. "Approve" and "Reject" buttons for each applicant. 2. Application status updates in real-time in the data file. | 3 | Finalizes the recruitment cycle.
PF_12 | Increase System Security | As a professor, I need enhanced system security , so that I can protect personal and teaching management data from leakage, tampering and loss. | Medium | 1 | 1. Two-factor login authentication; abnormal login reminders and forced logout. 2. Encrypted storage/transmission and desensitization display of sensitive data. | 5 | Hide sensitive data |  |  | 难道不应该是high吗
PF_13 | Password Management | As a professor, I want to change my password, so that I can protect my account from unauthorized access. | Medium | 1 | 1. Verify old password before allowing changes. 2. Update the password in the local storage file. | 2 | Personal data security.
PF_14 | Support Different Course Types | As a professor, I need the system to support TA management for different course types, so that I can allocate TA work rationally based on course teaching characteristics. | Low | 1 | 1. Support creating/customizing course type tags for new course setup. 2. Allow independent TA allocation for different classes and multi-TA collaboration. | 3 | Advanced function