## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Estimation | Notes | Date started (or planned) | Date finished (or planned)
TA端
TA_01 | Personal Profile Management | As an applicant, I want to maintain a persistent profile with my ID, name, phone number, gender, and other personal information, so that I don't need to re-type basic details for every recruitment cycle. | Must have | 1 | 1. Data can be saved and edited.2. Form fields are pre-filled with profile data during application. | 5 | Reduces repetitive input compared to the old survey.
TA_02 | Vacancy Browsing & Filtering | As an applicant, I want to see the total recruitment quota and current applicant count for each module or activity, so that I can judge my chances and make informed choices. | Should have | 1 | 1. Module or activity list displays "TAs Needed" and "Current Applicants".2. Real-time updates when new applications are submitted. | 3 | Essential for visibility.
TA_03 | Integrated Submission | As an applicant, I want to upload my CV directly within the application form, so that I can complete my application in one go without sending separate emails. | Should have | 1 | 1. Upload button integrated into the form process.2. Supports .pdf and .docx.3. Automatic link between the form data and the uploaded file. | 8 | Key Improvement: Removes the manual email workflow.
TA_04 | Password Reset | As an applicant, I want to reset my account password via my registered email, so that I can regain access to my profile if I forget it. | Should have | 1 | 1. "Forgot Password" link on the login page.2. System sends a reset code/link to the student email.3. User can securely set a new password. | 5 | Essential for account security and recovery.
TA_05 | Vacancy Categorization | As an applicant, I want to filter vacancies by type (e.g., Course TA vs. Invigilation/Activity), so that I can easily find short-term tasks or long-term roles. | Should have | 1 | 1. Provide a toggle or filter for "Module TA" and "General Activity".2. Each job card clearly displays its category. | 3 | Separates academic teaching from administrative support to streamline the searching process.
TA_06 | Activity Date Visibility | As an applicant for activity roles, I want to see the specific dates and time slots for tasks like invigilation, so that I can ensure they don't clash with my own exams. | Should have | 1 | 1. Activity roles display specific calendar dates instead of just "weekly hours".2. Applicants can select multiple specific time slots if the activity has several sessions. | 5 | Crucial for "Invigilation" which is date-specific.
TA_07 | Save as Draft | As an applicant, I want to save my progress while filling out the application, so that I can continue later without losing my entered data. | Could have | 2 | 1. "Save Draft" button available on the form.2. Users can resume unfinished applications from their dashboard. | 5 | Improve the user experience
TA_08 | Application Status Tracking | As an applicant, I want to see the real-time status of my application, so that I know if I am hired or rejected without contacting the office. | Could have | 2 | 1. A dashboard showing "Submitted", "Reviewing", or "Outcome".2. Notification upon status change. | 3 | Massive improvement in transparency.
TA_09 | Application Withdrawal | As an applicant, I want to withdraw a submitted application, so that I can cancel my request if I am no longer available or interested in the role. | Could have | 2 | 1. A "Withdraw" button is visible on the application dashboard.2. A confirmation prompt appears to prevent accidental withdrawal. | 3 | Clears the recruiter's list of inactive candidates.
TA_10 | Preference Selection | As an applicant, I want to select up to 3 preferred courses or activities and rank them by priority, so that the recruiter knows my top choices if I am qualified for multiple roles. | Want to have | 2 | 1. User can select up to 3 courses or activities.2. User can assign "Priority 1, 2, 3" to them. | 3 | Helps the system/recruiter resolve overlaps automatically.
老师端
PF_01 | Manage TA's Work | As a professor, I need to fully manage TAs' daily instructional support work in the system, so that I can track work progress clearly and improve the efficiency of instructional support work. | Must have | 1 | 1. Support assigning TA tasks with specified time, requirements and assessment criteria. 2. Enable real-time viewing of TA task status (Not Started/In Progress/Completed/Pending Review). |  | Basic requirement, must be done.
PF_02 | View Questionnaire Submissions | As a professor, I need a streamlined way to view questionnaire submissions, so that I can quickly know who enrolled in my course. | Must have | 1 | 1. Support filtering questionnaire submissions by the professor’s assigned courses with one click. 2. Ensure filtered student application data is synchronized in real time. |  | Concern from our teachers
PF_03 | User Registration & Role Selection | As a professor, I want to register an account and select my role, so that I can have the authority to manage TA recruitment. | Must have | 1 | 1. Provide fields for username, password, and role selection (MO). 2. Successfully save user data to a local text/JSON file. | 5 | Foundational for system access.
PF_04 | Simplify Approval Process | As a professor, I need simplified approval processes for TA-related matters, so that I can complete approvals quickly and avoid work delays. | Should have | 1 | 1. Provide a one-stop entrance for all pending approval items. 2. Realize real-time approval tracking and automatic result notifications. |  | Improve user using experience
PF_05 | Optimize UI Design | As a professor, I need an optimized system interface, so that I can find functions quickly and complete TA management operations efficiently. | Should have | 1 | 1. Modular interface with prominent core function entrances; support custom shortcuts. 2. Concise layout with rational button placement, no hidden key operations. |  | Improve user using experience
PF_06 | Increase System Stability | As a professor, I need a highly stable system, so that I can complete TA management work smoothly and ensure work continuity. | Should have | 1 | 1. Core page loading less than 2s for computer, 3s for mobile, no long-term loading failures. 2. Support ≥100 concurrent logins in peak periods with no freezes/data errors. |  | Avoid system breakdown
PF_07 | Applicant CV Review | As a professor, I want to view and download the CVs submitted by applicants, so that I can evaluate their academic and technical background. | Should have | 1 | 1. Clickable links to CV files (.txt/PDF) in the applicant list. 2. System retrieves files from the designated local path. | 3 | Key for selection process.
PF_08 | Applicant Selection & Approval | As a professor, I want to approve or reject TA applications, so that I can finalize the recruitment for my module. | Should have | 1 | 1. "Approve" and "Reject" buttons for each applicant. 2. Application status updates in real-time in the data file. | 3 | Finalizes the recruitment cycle.
PF_09 | Increase System Security | As a professor, I need enhanced system security , so that I can protect personal and teaching management data from leakage, tampering and loss. | Could have | 1 | 1. Two-factor login authentication; abnormal login reminders and forced logout. 2. Encrypted storage/transmission and desensitization display of sensitive data. |  | Hide sensitive data
PF_10 | Password Management | As a professor, I want to change my password, so that I can protect my account from unauthorized access. | Could have | 1 | 1. Verify old password before allowing changes. 2. Update the password in the local storage file. | 2 | Personal data security.
PF_11 | Support Mobile Device | As a professor, I need full mobile adaptation of the system, so that I can handle TA management work anytime in non-computer scenarios. | Could have | 1 | 1. Realize all computer-side viewing functions for core TA management data on mobile. 2. Achieve real-time data synchronization between mobile and computer ends. |  | Useful improvement
PF_12 | Support Different Course Types | As a professor, I need the system to support TA management for different course types, so that I can allocate TA work rationally based on course teaching characteristics. | Want to have | 1 | 1. Support creating/customizing course type tags for new course setup. 2. Allow independent TA allocation for different classes and multi-TA collaboration. |  | Advanced function